## Sheet1
Criteria Used to evaluate and group Projects:
0. Project Underway, continuation or completed
1. Large adverse affect on operating revenues, and\ or has a large adverse affect high paying jobs in district
2. Moderate to small adverse affect on Operating revenues and/or impacts lower paying jobs in the district
3. Improves overall operations, resulting in a better port, with better services, may or may not impact jobs
4. No impact to operations, does not generate revenue
CAPITAL IMPROVEMENT PLAN
| Capital Improvements | Cost Estimate | Original Timeline | Budget Year | Criteria | Rationale for group | Funding Source (Grant, Loan, OP Funds) | Current Status | Priority
NIT | Planning project to identify a mix of uses/opportunities that will maximize use of the terminal and adjacent vacant port-owned properties, and increase net revenues to the Port. Project completion primarily by Port staff | Original: $15,000 Current: $30,000 | 2019 | Not Necessary | 1 | This may or may not help improve the marketability of the site. | OP FUNDS, Potential Grant | Before we move forward with this effort again, we are currently working with a couple forest industries company, as it was originally identified by the strategic plan to be one of the main sources of future business. | 1
Mitigation Plan | Planning project to address mitigation needs of future capital projects and potential inventory of mitigation sites. Anticipated to be completed by Port staff in partnership with the Port of Toledo, Yaquina Bay users, NOAA, ODFW, and the USACE. Project completion primarily by Port staff | 25000 | 2019-2021 | Not Necessary | 0 | We are unable to bank for mitigations on a federal level. Therefore, mitigation plans should be done on a needed basis based on projects, but the Port should budget some amounts to cover for consultants. | OP FUNDS, Potential Grant | We have completed some small mitigation projects, as part of other projects. We looked at opportunities and discussed it with some of the permitting agencies. Until we have a permitted project it is hard to know what the mitigation needs are. It is very difficult to bank for mitigation. There may be some opportunities with the State, but not on a federal level. | As Needed
RV Park Annex Plan | Planning and conceptual design project to redesign and reconfigure the RV Park | 120000 | 2019-21 | 2023-24 | 1 | Does not affect high earners, but park is showing its age, major revenue could be lost. | Potential Grant Funds | We recently put out an RFP to select consultants to start on a plan. We realize that with recent emergency events related to utility issues and the overall wear and tear of the facilities, the need to move forward with this project has increase tremendously. | 1
Port Dock 5 Interim Improvements | Interim improvements to replace pier and improve dock. Approach pier replacement; replace 6 pilings; replace rods, whalers, rub boards, bumpers and triangles (PD 5C); replace rods, bumpers, rub boards and 6 whalers (PD 5B); replace rods and rub boards (PD 5x); new power pedestals | 3500000 | 2019-22 | 2021-24 | 1 | There are still some projects left to complete, and they are crucial to the Port operations and should be finished as soon as practical. | OP FUNDS | Permitting repairs to PD5A, which will include rewiring of all PD5. Pedestals are on hand, awaiting permits to add the PD5A replacement to the project. The approach pier is completed. We are looking at installation of about 2 pilings, not 6. | 1
Port dock 7 Interim Improvements | Interim improvements prior to reconfiguration /replacement: Miscellaneous float and pile improvements | 348000 | 2019-22 | 2022-23 | 1 | Some of the repairs are crucial to keep PD7 in operations until replacement. | OP FUNDS | applied for permits to drive 15 new pilings on Port Dock 7 E & F, install temporary new floats to bridge the gap until replacement of the entire Port Dock 7. Anticipate completing pile driving and dock replacement during FY 2023-24. Dock parts have already been ordered. | 1
Reconfiguration and Reconstruction of Marina | Complete reconstruction and reconfiguration of commercial marina, including Port Docks 3 and 7, Upland Improvements, Swede's Dock and Commercial Marina channel | Original Budget: $14,75,000 New budget: $20,000,000 Plus Channel $5,000,000 | 2019-24 | 2024-2025 | 1 | PD7 is at end of life, high wage earners will move elsewhere, major economic impact to Port and community | Grant (s)/Op Fund | We are currently under contract with DOWL Engineers, and underway on planning and design and permitting for the redesign and replacement of Port Dock 7. Replacement of the Hoist Dock is included in this project as an add-alternate. Sediment sampling will be some of the most expensive costs in the planning process, and we intend to be complete with the sampling in the Commercial Marina during summer, 2023. The Port and the US Army Corps is currently working on a Feasibility Study to assess probability of extending and deepening the channel to the Commercial Marina. | 1
Fishing Pier Improvement | Identify replacement strategy and design new fishing pier | 2900000 | 2022 | 2024-2027 | 4 | Although we recognize the fishing pier has great value for the community, it does not improve the overall operations or revenues of the Port, it does not create jobs or impact the overall economy of the community. This project will provide greater value by combining it with the replacement of PD7 where it will support mitigation opportunity and possible use of grants. | Grants | This project is expected to be completed along PD7 reconstruction. We are currently under contract with DOWL Engineers and underway on planning for this project. Have been taking community input since March, 2023 on design criteria, held meeting with the public to get input. Sediment Sampling on this side of the project tentative for summer, 2024. Since we intent to use some of the fishing pier replacement for the Port Dock 7 mitigation, we are trying to include parts of this plan on the Port Dock 7 Plan. We recently had a listening session open to the public. We are still opened for comments in our website. | 4
Rogue Seawall Repair | Repair Rogue seawall based on Engineers Report | 1400000 | 2019-21 | 2022-24 | 1 | Major economic loss, Rogue brewery could move, causing large loss to community and revenue to the Port. Many come to community to visit Rogue. | Grant received | We received $1.1 Million dollars from the State. We are working on finalizing permit, so the work can be completed within this winter's inward work. | 1
Electric Work, Fuel Tanks and Security Cameras Replacements and Upgrades (Safety and Security) | South Beach Marina electric load centers; South Beach fuel tank replacement; relocate/replace hoist dock electrical lines; consolidate and upgrade total security camera network port-wide. | 2560000 | 2019-2024 | 2021-24 | 3 | These projects mostly affect the operations of the Port and the functionality of its assets. Because of that it is hard to obtain grants other than security cameras and lighting. | OP-Funds/Some grants | Although the South Beach Marina electric load centers was set to be completed altogether in 3 years, the Port went ahead and completed the project all at once. The total cost came under budget at around $700K. We plan on including the fuel tank replacement and the hoist dock electrical lines to our 2022-23 budget. We have made the effort to install new cameras to our facilities every year through a grant program from SDAO. Anticipate replacing gates on the South Beach Docks, and transitioning to a proximity card locking system to begin in summer, 2023 and complete over the course of three years. Project is spread out to monitor the effectiveness of the new locks, and make changes as we learn more. We will continue to make improvements and upgrading our security efforts. | 3
NIT Improvements | Grading of Port's 9-acre lot (does not include wetland mitigation); asphalt lot west of shop, behind shop, and near the east entrance; asphalt nw corner of laydown area; installation of waste oil collection tank; mutually beneficial project, as required by development agreement with McLean Point developer | Grading: $153,000; Asphalt: $234,000; Tank; $45,000, Other: $50,000. Total NIT $482,000 Plus removal of dredge Material $200,000 | 2019-2023 | 2021-2022 | 0 | We are currently finishing the grading work and have not much choice on completing some projects that have been agreed under the agreement with Rondy. | OP Funds | We completed the asphalt paving to the lot west of the shop. We still have additional paving to do. We seleted a contractor to start working on the grading of the 9 acres. That may include working with Rondy's to upgrade the drain lines to their property. Fortunately, we will not need to mitigate the wetlands. We are still working with Rondy's on the mutually beneficial project. At this point the port has budgeted to remove the dredge sand from their property. | 3
RV Annex | Final plans, new RV Annex; New RV Annex construction | 2620000 | 2019-2022 | 2023-25 | 1 | Does not affect high earners, but park is showing its age, major revenue could be lost. | OP Funds/Grants | RFP is out to start to work on the plan. Once plans are completed we will better know how to proceed. | 3
Port Admin Building+A21:J44 | Build a new building for administrative staff and commission meetings | 2400000 | N/A | 2021-23 | 0 | Although this was not originally included on the Strategic Business Plan, the project has been discussed and even planned in a couple occasions, because the need to replace a temporary building that is now almost 10 years old. | Loan/Op Funds | Unfortunately there were delays due to supply issues, but fortunately materials have been received and building was just completed. Staff has moved into the building on 05/05/23. | Completed
South Beach Marina Improvements | Repair to South Beach Marina Buildings |  | N/A | 2021-22 | 0 | These major maintenance items were never added to Strategic Business Plan | Op Funds | We have replaced siding and painted all restrooms and showers, Marina Store, Maintenance Shop, and are already under contract to paint the distillery and RV Park Office during summer, 2023. After painting is complete in summer, 2023, all buildings in the marina have been completed; the old building at the Rogue Brewery will be the next big siding/paint/roofing project. | Completed
South Beach Marina Storm Water | Emergency Storm Water Work | 345000 | N/A | 2020-2021 | 0 | This was an emergency project that was completely unexpected. | Op Funds | We completed an emergency project to address the storm water issue at South Beach Marina. Unfortunately, new sinkholes have been forming due to other storm water issues, which may create additional costs. | Completed
343 SW Bay Blvd Removal | Emergency Building and Dock Removal | 200000 | N/A | 2021-23 | 0 | The building was removed due to safety issues. We are hoping to remove the dock as a mitigation project. | Op Funds | Completed emergency removal of building atop the pier, and sold the property | Completed
North Commercial Oil Tank Removal | Emergency Commercial Oil Tank Removal and Upgrade | Tank: $200000 Building $86,000 | N/A | 2021-23 | 0 | Old Tank was removed due to leaking issue. We are researching on a replacement | Op Funds | We had an emergency removal of the Oil Tank/Bilge Collection at North Commercial. We foresee replacement of the tank; project may be combined with Port Dock 7 replacement depending on funding. | 1
South Beach Marina GFI Breaker Installation | The GFI Breakers have all been purchased, moving towards installation | 115000 | N/A | 2021-22 | 0 | The supply chain has caused some issues, but project is currently underway. | OP Funds | As part of replacing the load centers on South Beach Marina, the Port decided to also replace the breakers in the power pedestals with GFI breakers. | Completed
NIT Conditional Assessment | Conditional Assessment | 230000 | N/A | 2022-24 | 2 | The Pilings at NIT RoRo dock needs assessment and most likely repair and/or treatment to extend their life. | Op Funds | Assessment has been completed. Now the Port is searching for a source of funds to do the proper repairs. | Completed
NIT Repair of RORO dock Pilings | Repair of RORO dock Pilings | 687000 | N/A | 2023-24 | 1 | Assessment has been completed and some Pilings at NIT RoRo dock needs repairs and/or treatment to extend their life. | Op Funds | A completion of Joint Permit Application is underway, anticipate repairs and piling wraps to be installed winter 2023-24A request has been made to federal legislation for Congressially Directed Spending FY 24. Rep. Val Hoyle currently has this project listed as one of her 15 projects priorities. | 1
South Beach Marina Outfall Sleaving | Repair/Maintenance of Outfall at South Beach Marina | $230,000; $500,000 | N/A | 2022-23 | 3 | The outfall at the marina needs to be addressed to avoid future issues (sinking). | Op Funds | Some work has been completed last year. Unfortunately, more sinkholes have showed up. We are assessing the issues and working on the outfalls before it becomes bigger a problem. | 1
South Beach Buildings (previous fruit processing facility) | Demolishing, rebuilding, new roofs, new siding | 300000 | N/A | 2022-23 | 2 | South Beach buildings are in pretty bad shape. We are in the process of leasing two of the buildings, but they need new roof and sidings. We also should demolish the unhabitable building and instead build a smaller building to house all the power to the property. | Op Funds | Leased one building to Newport Fab Shop, repaired walls, exterior doors, and roof, rewired building. One building is awaiting demolition and construction of a shed for the the utilities, main building still needs siding. | 2
CM and NIT Forklift Replacement | 1 Forklift has passed it's replacement cycle based on hours used. | 128000 | N/A | 2022-23 | 1 | We deferred purchase of a new lift for 2 years; our forklifts in the Marina are heavily used and they must be reliable to keep the hoist dock working. We are well over the 6,000 limit for replacement on two forklifts | Op Funds | Purchased in FY 2022-23, received new forklift on 09MAY 2023. The Port received a grant from Business Oregon that allowed us to order an additional $128K fork lift that will mainly reside at the Terminal. Unfortunately, it may be a year before we receive the equipment | 1
CM Shop Expansion | Expand shop at Commercial Office | 30000 | N/A | 2022-23 | 3 | Need office space for Harbormaster, no confidential conversations can be held with current configuration. | Op Funds | Commercial Marina shop is not configured to be a service location, and also lacks adequate space for personnel. Project has been deferred in favor of dock work in years past. | 3
Dredge Swedes Dock | Dredge Swedes Dock | 150000 | N/A | 2023-25 | 3 | It hasn’t been dredged in over 33 years and it is starting to show. | Op Funds | May potentially combine this project with PD7 replacement, we may also benefit from Corps Section 107 project, which is yet to be determined. | 4
CM HOIST Dock Fenders | Replace Hoist Dock Fenders | 35000 | N/A | 2023-24 | 3 |  | Op Funds | Fender pilings are increasingly in poor condition. May combine with PD7 replacement project. | 3
CM PD 3 Access Power and Water | Remove PD 3 Power and Water Access from Neighboring Property | 250000 | N/A | 2025-27 | 3 | Current Power and Water is attached to the neighboring building. We don't know the condition of the pilings. | Op Funds | To be completed when Port Dock 5 is rewired. | 4
SB HVAC system | Replace HVAC System at SB Shop | 15000 | N/A | 2024-25 | 3 | HVAC systems are old and soon in need of repair | Op Funds |  | 4
SB End ties A-E docks | Replace Rods and Whalers at end ties A-E in SB Docks | 100000 | N/A | 2022-24 | 3 | The end ties are the largest single berths in South Beach. They ''re used for the bigger vessels that use the marina, and are in need of rods and whalers to stay in operation | Op Funds | Completed B Dock. A, C, D, and E will be completed over the next two years. | 1
CM Swedes Ddock 12-14 Pilings | Replace pilings at Swedes Dock | 215000 | N/A | 2024-24 | 1 | The Dock is at the end of its service life and in need of replacement | Op Funds | Emergency piling replacement was completed during winter 2021-22. Other piling replacement, removal of boathouse, and dock replacement will take place alongside progression of PD7 replacement. | 3
SB Asphalt Overlay | Asphalt Overlay at SB | 100000 | N/A | 2023-24 | 3 | The asphalt in the area where Seafood & Wine is held along with other festivals has been patched again and again due to the impact of tent stakes and concrete curbing. It needs to be repaved. | Op Funds |  | 3
Rogue Gutter Replacement | Replace Gutters at Rogue Building | 100000 | N/A | 2022-24 | 1 | There are currently holes in the eves on the building. These need to be repaired to prevent impacts to the walls. | Op Funds | Received limited funding from insurance for flashing repair; siding will also need replaced on west end of building. | 1
SB Expo Center |  | 30000 | N/A | 2022-23 | 2 | Facility to enhance the recreational theme of South Beach and add attractions for tourists. Would bolster hotel business and tourism in the region. | Op Fund/Grants | This project has been put on hold due to other projects priority. We will continue to evaluate opportunities to revisit this project. | 2
SB Forklift replacement | Purchase New Forklift for SB | 40000 | N/A | 2024-25 | 3 | Current forklift is reaching the top end of operating hours |  | To be purchased 2024-25 | 2
Fillet Tables |  | 130000 | N/A | 2022-23 | 3 | Tables are over crowded and we need to add capacity | Op Funds/Grants | We recently received a grant from Business oregon for about $47K out of $175K to be used for the fillet tables. Staff has started working on moving forward on this project, which will try to avoid too much disturbance to users during the busy season. | 1
NIT Crane replacement | Crane is at max capacity, in order to handle cargo or other heavy loads will have to be replace | 700000 | N/A | 2022-23 | 1 | This is new potential revenue to Port, but could also affect high income earners should Crane fail | Grant - MARAD | We are still trying to find funds to pay for a new crane. Unfortunately, we keep having more and more issues with the current crane and may have to expedite the replacement.
North Commercial Cranes Replacement |  | 160000 | N/A | 2024-26 | 3 | We need to consider replacing North Commercial cranes within the next 2-3 years | Op Funds | Crane service could be achieved with a carry-deck crane, but would require an indoor storage and upgrade of Hoist Dock. Could be completed with rebuild of Hoist Dock. | 4
Port vehicles | Replace aging vehicles with high mileage all throughout the Port | 100000 | N/A | 2022-24 | 3 | Vehicle breakdowns could cause Operational issues | Op Funds | Two vehicles has been replaced. We have also put a request with Business Oregon who is working on a joint ODOT Carbon Reduction Program/New Equipment and have added a couple more vehicles. | 3
NIT Equipment plus Building | Purchase Terminal Equipament and Storage Building | 4305125 | N/A | 2022-23 | 1 | In order to establish future cargo operations, the Port should consider obtaining some equipment and a building to house such equipment. We should consider applying for future MARAD grants. | Op Funds/MARAD | The Port once again applied for the PIDP grant through MARAD to purchase two loaders, grading of the 9 acres and fence 3 acres of land. We should have the results in the Fall. | 2
NOAA Dredging | Dredge NOAA's Berth | 1099000 | N/A | 2022-23 | 1 | We have an obligation to dredge NOAA. We have skipped this year, but will be required to dredge in the following year. | Op Funds | After ODFW changed shorten the inwater work by 15 days, we had to request a variance to dredge at the end of the summer or early fall. The permit was granted and the contractor has been secure. Dredging most likely will occur in October. | 1
NIT dredging | Dredge NIT's Berth | 1100000 | N/A | 2022-23 | 1 | NIT will need to be dredged within the next 1-2 years. | Op Funds | We have postpone dredging of NIT due to lack of permit, which we are still waiting to obtain and cost and because this is maintenance dredge and the condition is still acceptable. We will try to obtain grant funds and will schedule dredging in the next couple years. | 1
South Beach Marina Dredging | Dredge South Beach Marina | $1,500,000 - $2,000,000 | N/A | 2022-24 | 1 | South Beach Marina will need to be dredged within the next 1-2 years. Coordinated efforts will be made to dredge the marina at the same time as we dredge NOAA if we are able to obtain permits in time. | Op Funds/OSMB | We are still trying to obtain a permit, which it is a bit more complicated for this location as it hasn't been dredged for many years. | 2
South Beach Operations | Expand shop at SB | 30000 | N/A | 2023-24 | 3 | Need office space for Harbormaster, no confidential conversations can be held with current configuration. | OP Funds | We are still evaluating the need versus priority | 4
South Beach Marina Service Dock near the Rogue Seawall needs repairs | The current dock is not useable | 400000 | N/A | 2022-23 | 1 | The South Beach Marina service dock needs some major repairs. We spoke to the Oregon State Marine Board, but they are unlikely to fund this project, unless the majority of the dock is to service transient boats, which it is not the case here. We are hoping to complete this work in parallel with the Rogue Seawall Repairs. | Op Funds | We have been looking for funding sources, but at one point we may need to use port funds if necessary. | 1
CM Hoist Reconfiguration | Reconfigure Hoist Dock and Move CM Building with Loading Dock plus small mobile crane | 4000000 | N/A | 2024-27 | 1 | A reconfiguration of the hoist dock would eventually make more sense for overall operations | Op Funds/Grants | Best overall option for longevity and improved usage; pending funding. | 4
Replace Equipments | Replace worn equipments throughout the Port | Tugboat Haul Out $10,000; Trash Compactors CM: $37,000, SB: $37,000 | NA | 2023-24 | 3 | These are aging or worn out equipment that need replacement | Op Funds | SB side-by-side was purchased during FY 2022-23. Dumpsters were replaced in FY 2022-23.Tugboat Haulout will be more expensive, and compactors are critical to be replaced no later than 2023-24. | 4
NEW PROJECTS ADDED SINCE FY 2022-23
SB New Building | Build or rebuild new building for Tenant if opportunity arises | 1000000 | N/A | 2023-26 |  | We don't have any buildings available in SB or at the Port for that matter. Should an opportunity to lease a building to customer, we should consider building a new one. | Loan/Op Funds | We don't currently have a prospect tenant, but we had some in the past. A new building will only be considered if we have an interested party. | 4